## Tasks and Timeline
Sauce & Spoon Project Plan
Task | Notes | Start Date | Due Date | Duration (Days) | Task Owner | Status | PHASE ONE | [14 empty] | PHASE TWO | [14 empty] | PHASE THREE | [14 empty] | PHASE FOUR
[7 empty] | WEEK 1 |  |  |  |  | WEEK 2 |  |  |  |  | WEEK 3 |  |  |  |  | WEEK 4 |  |  |  |  | WEEK 5 |  |  |  |  | WEEK 6 |  |  |  |  | WEEK 7 |  |  |  |  | WEEK 8 |  |  |  |  | WEEK 9 |  |  |  |  | WEEK 10 |  |  |  |  | WEEK 11 |  |  |  |  | WEEK 12
[7 empty] | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F
Milestone: Procure Tablets
Collaborate with the GM at the Downtown site to determine the quantity of tablets required. |  |  |  | 0.5 | bar: WEEK 1 M
Collaborate with GM at the North location to identify the number of tablets needed. |  |  |  | .0.5 | bar: WEEK 1 M
Decide if we will purchase and store backup tablets for emergencies |  |  |  | 0.5 | bar: WEEK 1 M
Assess available tablet options and specs from the supplier that meet appropriate requirements |  |  |  | 0.5 | bar: WEEK 1 M
Create contract and statements of work for tablet vendor |  |  |  | 1 | bar: WEEK 1 T
Purchase and take delivery of the appropriate quantity of tablets. | Our originally ordered tablets were unable to arrive in time for launch and should come in a few weeks after launch because of disrupted supply lines due to overseas and a series of storms. Though, Tablets will be replaced with newer ones due to this with additional cost. |  |  | 12 | bar: WEEK 1 W to WEEK 3 T
Milestone: Prepare for rollout with Internal Teams
Link up the marketing team with Terrific Tablets to handle branding and create a digital menu design. |  |  |  | 0.5 | bar: WEEK 1 W
Collaborate with Carter to explore the possibility of updating the menu. | Can we delay this? It may hinder the selection of menu items and the display of coupon values on the tablets. |  |  | 9 | Carter | bar: WEEK 1 R to WEEK 3 T
Incorporate highlighted menu items and coupon values into the tablets. | The outcome will rely on the marketing team's designs, along with pinpointing prominent menu items and discount values from Peta. Additionally, it could be influenced by the possibility of a menu renovation from Carter. |  |  | 1 | Deanna, Carter, and Marketing | bar: WEEK 3 T
Work with the tablet supplier to recognize typical problems and the time it takes to fix tablet issues. |  |  |  | 2 | Peta | bar: WEEK 1 R to WEEK 2 F
Create an in-house policy and guide for resolving tablet-related problems during deployment and use. |  |  |  | 3 | Peta | bar: WEEK 1 R to WEEK 2 F
Evaluate the necessary efforts to ensure that the tablets are effortlessly integrated with the existing POS and host system. | In order to work with the tablets, upgrade the FlatPlate OS as it needs to be on version 3.0 |  |  | 3 | bar: WEEK 2 T to WEEK 2 F
Milestone: Tablet Training
Create a program for training and a guide for deployment. |  |  |  | 6 | Peta | bar: WEEK 1 R to WEEK 2 F
Organize a meeting before the training to introduce the tablets and the upcoming changes. |  |  |  | 1 | Seydou | bar: WEEK 1 F; WEEK 2 W to WEEK 2 F
Seydou will educate the General Managers and other essential personnel on the usage of tablets. |  |  |  | 2 | Seydou
Collaborate with the General Managers to schedule and hold meetings, discuss the deployment, and address any queries or issues. | Make sure to monitor staff response and address questions |  |  | 7 | bar: WEEK 2 M to WEEK 4 T
Milestone: Tablet Installation
Determine the bar section tables that require correct wiring by an electrician. |  |  |  | 0 | bar: WEEK 3 T
Install one tablet to guarantee correct placement and identify any possible problems. |  |  |  | 0.5 | bar: WEEK 3 T
Recruit an electrician to wire the necessary tables at the Downtown venue. | Address any potential issues by installing one tablet first and note any issues for a day. |  |  | 3 | bar: WEEK 3 T to WEEK 3 R
Recruit an electrician to wire the appropriate tables at the North location. | Address any potential issues by installing one tablet first and note any issues for a day. |  |  | 3 | bar: WEEK 3 T to WEEK 3 R
Milestone: Test Run
Conduct a trial with the staff, family, and friends to simulate the complete service. |  |  |  | 0.5 | bar: WEEK 4 M
Gather feedback from the trial and identify potential areas for improvement. |  |  |  | 1 | bar: WEEK 4 T
Apply the feedback obtained from the trial run. |  |  |  | 3 | bar: WEEK 4 W to WEEK 4 F
Milestone: Launch Day
Arrange a date for the launch day. |  |  |  | 0.5 | bar: WEEK 1 M
Get ready for the launch day by collaborating with and recognizing any remaining requirements from the General Managers. |  |  |  | 2 | bar: WEEK 3 W to WEEK 3 R
Launch the project on the decided launch day! |  |  |  | 0.5 | bar: WEEK 4 T
Milestone: Upgrad Devices Post-Launch
Replace the plugs for the new tablets. | Our originally ordered tablets were unable to arrive in time for launch and should come in a few weeks after launch because of disrupted supply lines due to overseas and a series of storms. Though, Tablets will be replaced with newer ones due to this with additional cost. |  |  | 2 | bar: WEEK 5 T to WEEK 5 W

## Task Brainstorm
Task Brainstorm
Task | Notes | Estimated Duration (Days) | Optimistic | Most Likely | Pessimistic | Confidence Rating (H/M/L) | Known Dates
Milestone: Procure Tablets
Collaborate with the GM at the Downtown site to determine the quantity of tablets required. |  | 0.5 | 0.5 | 0.5 | 1 | H
Collaborate with GM at the North location to identify the number of tablets needed. |  | 0.5 | 0.5 | 0.5 | 1 | H
Decide if we will purchase and store backup tablets for emergencies |  | 0.5 | 0.5 | 0.5 | 1 | H
Assess available tablet options and specs from the supplier that meet appropriate requirements |  | 1 | 1 | 1 | 2 | H
Create contract and statements of work for tablet vendor |  | 2 | 1 | 2 | 3 | H
Purchase and take delivery of the appropriate quantity of tablets. | Our originally ordered tablets were unable to arrive in time for launch and should come in a few weeks after launch because of disrupted supply lines due to overseas and a series of storms. Though, Tablets will be replaced with newer ones due to this with additional cost. | 12 | 7 | 10 | 14 | H
Milestone: Installation and setup
Link up the marketing team with Terrific Tablets to handle branding and create a digital menu design. |  | 0.5 | 0.5 | 0.5 | 1 | H
Work with the tablet supplier to recognize typical problems and the time it takes to fix tablet issues. |  | 2 | 1 | 2 | 4 | H
Develop an in-house policy and guide for resolving tablet-related problems during deployment and use. |  | 3 | 1 | 2 | 4 | M
Evaluate the necessary efforts to ensure that the tablets are effortlessly integrated with the existing POS and host system. | In order to work with the tablets, upgrade the FlatPlate OS as it needs to be on version 3.0 | 3 | 1 | 3 | 4 | L
Find a storage location for backup tablets. |  | 0.5 | 0.5 | 0.5 | 1 | H
Determine the bar section tables that require correct wiring by an electrician. |  | 0.5 | 0.5 | 0.5 | 1 | H
Install one tablet to guarantee correct placement and identify any possible problems. |  | 0.5 | 0.5 | 0.5 | 1 | M
Recruit an electrician to wire the necessary tables at the Downtown venue. | Address any potential issues by installing one tablet first and note any issues for a day. | 3 | 2 | 3 | 4 | M
Recruit an electrician to wire the appropriate tables at the North location. | Address any potential issues by installing one tablet first and note any issues for a day. | 3 | 2 | 3 | 4 | M
Add featured menu items and coupon values to tablets | Dependent on marketing team designs, as well as identifying featured menu items and coupon values from Peta. Would also be impacted by potential menu revamp from Carter. | 1 | 0.5 | 1 | 2 | M
Work with Carter on possible menu revamp | Is this something that we can hold off on? It potentially blocks the decision for featured menu items and coupon values to display on the tablets | 10 | 4 | 10 | 14 | M
Milestone: Tablet Training
Create a program for training and a guide for deployment. |  | 6 | 6 | 7 | 10 | H
Organize a meeting before the training to introduce the tablets and the upcoming changes. |  | 1 | 1 | 1 | 2 | H
Seydou will educate the General Managers and other essential personnel on the usage of tablets. |  | 2 | 2 | 2 | 3 | H
Collaborate with the General Managers to schedule and hold meetings, discuss the deployment, and address any queries or issues. | Make sure to monitor staff response and address questions | 7 | 7 | 10 | 14 | L
Milestone: Test Run
Conduct a trial with the staff, family, and friends to simulate the complete service. |  | 0.5 | 0.5 | 0.5 | 1 | H
Gather feedback from the trial and identify potential areas for improvement. |  | 1 | 0.5 | 1 | 2 | M
Apply the feedback obtained from the trial run. | Feedback might range from updating the menu to processing change | 3 | 1 | 2 | 4 | L
Milestone: Launch Day
Arrange a date for the launch day. |  | 0.5 | 0.5 | 0.5 | 1 | H
Get ready for the launch day by collaborating with and recognizing any remaining requirements from the General Managers. |  | 2 | 1 | 2 | 4 | H
Launch the project on the decided launch day! |  | 0.5 | 0.5 | 0.5 | 0 | H
Milestone: Upgrad Devices Post-Launch | Our originally ordered tablets were unable to arrive in time for launch and should come in a few weeks after launch because of disrupted supply lines due to overseas and a series of storms. Though, Tablets will be replaced with newer ones due to this with additional cost.
Change plugs for new tablets.

## Additional Resources
Additional Resources
Title | Link | Date Added | Notes
Restaurant Tablets- Is It Worth the Investment? |  | 2021-06-15 | Source kitchen monitors to streamline orders to allow the entire kitchen staff to view incoming requests without the struggle of deciphering different servers' handwriting
3 reasons why a tablet ordering system will ruin your restaurant |  | 2021-06-15 | Purchase backup tablets. What happens when a tablet breaks?

## Survey Questions
Survey Questions
Quality Standards |  |  |  |  | Question Answer Options (depends on question type)
Criteria/Description | Evaluation Questions | Evaluation Indicators | Survey Question | Question Type | Option #1 | Option #2 | Option #3 | Option #4 | Option #5
Average ticket time for appetizers ~ 8 minutes and 12-15 minutes for entrees. | Can the back-end staff reasonably accomodate a turn-around time of around eight minutes for appetizers and 12-15 minutes for entrees? | Assess order flow and fulfillment. Track time orders are placed to when they are served. Does the tablet software track this data over time? | How long did it take for you to receive your appetizers? | Multiple choice | 5-10 minutes | 10-15 minutes | more than 15 minutes
Average ticket time for appetizers ~ 8 minutes and 12-15 minutes for entrees. | Can the back-end staff reasonably accomodate a turn-around time of around eight minutes for appetizers and 12-15 minutes for entrees? | Assess order flow and fulfillment. Track time orders are placed to when they are served. Does the tablet software track this data over time? | How long did it take for you to receive your entrees? | Multiple choice | 5-10 minutes | 10-15 minutes | more than 15 minutes
Checkout time of one minute or less. | What are the benefits to customer experience when they are able to checkout in one minute or less? | Include optional surevy at the end of payment to collect user feedback | How long did it take you to complete the checkout process today? | Multiple choice | less than a minute | 1-3 minutes | more than 3 minutes
Checkout time of one minute or less. | What are the benefits to customer experience when they are able to checkout in one minute or less? | Include optional surevy at the end of payment to collect user feedback | How satisfied are you using the tablet to checkout? | Scaled | Very Unsatisfied | Unsatisfied | Neutral | Satisfied | Very Satisfied
Less than 5% of customers who use the tablets report technical issues each week | What are the common technical issues that arise with tablet usage and how can they be mitigated/avoided/resolved? | Research frequent tablet issues and identify ways to approach those issues should they arise. Train staff on those issues and how to resolve. | Did you encounter any issues using the tablet? | Yes/No | Yes. Please explain: | No
Less than 5% of customers who use the tablets report technical issues each week | What are the common technical issues that arise with tablet usage and how can they be mitigated/avoided/resolved? | Research frequent tablet issues and identify ways to approach those issues should they arise. Train staff on those issues and how to resolve. | How was your experience using the tablet to order your meal today? | Open-ended | Please explain:
100% order accuracy | How can we assess customer satisfaction with their meal? | Ask customer via survey if they enjoyed their meal and if they were able to order exactly what they wanted with the tablet | Were you satisfied with your meal today? | Yes/No | Yes | No
100% order accuracy | How can we assess customer satisfaction with their meal? | Ask customer via survey if they enjoyed their meal and if they were able to order exactly what they wanted with the tablet | Were you able to order exactly what you wanted? If no, please explain. | Yes/No | Yes | No. Please explain:
Average wait time of ten minutes or less before customers are seated | How can we reduce the wait time to under ten minutes? | Track wait times in host system to ensure customers are being seated in under ten minutes. | How long did you have to wait before being seated today? | Multiple choice | 0-5 min | 5-10 min | 10-15min | 15 or more min
Average wait time of ten minutes or less before customers are seated | How can we reduce the wait time to under ten minutes? | Track wait times in host system to ensure customers are being seated in under ten minutes. | Were you satisfied with your wait time today? | Scaled | Very Unsatisfied | Unsatisfied | Neutral | Satisfied | Very Satisfied

## Quality and Evaluation
Quality and Evaluation
Quality Standards | Quality Standards
Category | Criteria/Description | Evaluation Questions | Evaluation Indicators | Criteria Met?
Customer Satisfaction - faster, more efficient experience | Average ticket time for appetizers ~ 8 minutes and 12-15 minutes for entrees. | Can the back-end staff reasonably accomodate a turn-around time of around eight minutes for appetizers and 12-15 minutes for entrees? | Assess order flow and fulfillment. Track time orders are placed to when they are served. Does the tablet software track this data over time? | FALSE
Customer Satisfaction - faster, more efficient experience | Checkout time of one minute or less. | What are the benefits to customer experience when they are able to checkout in one minute or less? | Include optional surevy at the end of payment to collect user feedback | FALSE
Customer Satisfaction - faster, more efficient experience | Less than 5% of customers who use the tablets report technical issues each week | What are the common technical issues that arise with tablet usage and how can they be mitigated/avoided/resolved? | Research frequent tablet issues and identify ways to approach those issues should they arise. Train staff on those issues and how to resolve. | FALSE
Customer Satisfaction - faster, more efficient experience | 100% order accuracy |  |  | FALSE
Customer Satisfaction - faster, more efficient experience | Average wait time of ten minutes or less before customers are seated | How can we reduce the wait time to under ten minutes? | Track wait times in host system to ensure customers are being seated in under ten minutes. | FALSE